## README
Metro Buddy - plan workbook
Spec | metro-buddy-spec.md
Ontology | metro-buddy-ontology.md
Tabs
Features | Feature catalog. Task count, estimate and done count are formulas from Tasks.
Tasks | Build tasks in order. Edit the yellow Status / Owner columns.
Phase Summary | Effort and progress per phase (formulas).
Entities | Data model entities by domain with retention.
Fields | Every field: type, constraints, privacy class.
Enums | Enum types and allowed values.
Phases | P0 Foundation ¦ P1 Bowls ¦ P2 Chat ¦ P3 Travel Buddy (MVP launch) ¦ P4 Vent Studio ¦ P5 Trust & growth ¦ P6 Later
Priority | MoSCoW: Must / Should / Could
Privacy class | P0 system/public, P1 pseudonymous, P2 personal (owner only), P3 sensitive (hashed/encrypted)
Assumption | Est (days) = rough single-developer estimates made by Claude for planning only; revise with your team.

## Features
Feature ID | Module | Feature | Description | Phase | Priority | User value | Depends on | Tasks | Est (days) | Tasks done
F01 | Identity | Phone OTP login | Indian mobile number + 6-digit OTP via MSG91; JWT access + rotating refresh token in secure store | P0 | Must | Frictionless, no password
F02 | Identity | Anonymous persona | Auto alias (e.g. 'Chai Comet 27') + generated avatar; re-roll at signup; alias change once / 30 days | P0 | Must | Be yourself without being exposed | F01
F03 | Identity | Vibe profile | Pick 3-10 vibe tags (chatty/quiet, music, cricket, books, startup talk...) and intents (vent, listen, travel buddy, friends) | P0 | Must | Find people like you | F02
F04 | Identity | Home metro setup | City, home station, work/college station, usual line | P0 | Must | Personalised bowls and matches | F02
F05 | Identity | Age gate & consents | 18+ declaration, DPDP itemised consents (core, matching, AI processing, analytics), privacy policy acceptance | P0 | Must | Trust and legal compliance | F01
F06 | Identity | Device integrity | Play Integrity / App Attest check at signup to cut bot and multi-account abuse | P6 | Could | Fewer fake accounts | F01
F07 | Identity | Selfie verification badge | Liveness selfie via KYC vendor; only a 'verified' boolean is kept, the image is discarded | P6 | Could | Safer travel matches | F01
F08 | Identity | Reveal ladder | Mutual, step-wise reveal per conversation: first name -> photo -> contact; revocable | P5 | Should | Turn strangers into friends safely | F20
F10 | Bowls | Bowl discovery & join | Auto-suggested bowls by line, station, office hub, college and topic; join/leave | P1 | Must | Find your crowd | F04
F11 | Bowls | Posts | Anonymous text/image/poll posts with flair, in a bowl | P1 | Must | Vent and share | F10,F24
F12 | Bowls | Comments & votes | Threaded comments (2 levels), up/down votes, OP badge | P1 | Must | Discussion | F11
F13 | Bowls | Feed ranking | Home and bowl feeds with Hot/New/Top; hot score precomputed every 5 min | P1 | Must | Relevant content | F11
F14 | Bowls | User-created bowls | Trusted users can create bowls and become bowl mods | P5 | Should | Community ownership | F52
F15 | Bowls | Daily prompts | Daily themed prompt per city ('Plan ditched today?') | P1 | Should | Habit and conversation starter | F11
F20 | Chat | DM requests | 1:1 chat starts as a request; recipient accepts/ignores/blocks | P2 | Must | No unsolicited messages | F02,F50
F21 | Chat | Group chats | Private groups up to 50 members with admins and invite links | P2 | Must | Talk with your circle | F23
F22 | Chat | Live discussion rooms | Time-boxed public text rooms on a topic, linked to a bowl; slow mode | P2 | Should | Group discussion on what's hot | F23
F23 | Chat | Realtime messaging | WebSocket gateway, Redis fan-out, typing, receipts, offline sync, optimistic sends | P2 | Must | Feels instant | F01
F24 | Chat | PII masking | Regex + rules masker on all UGC before persist; async LLM second pass; encrypted raw vault with 90-day TTL | P1 | Must | Identity stays hidden
F25 | Chat | Images in chat | Image messages, blurred until tapped, NSFW scan, EXIF strip | P5 | Could | Richer chat | F23
F26 | Chat | Disappearing messages | Per-conversation TTL (24h / 7d) | P5 | Could | Less digital footprint | F23
F30 | Vent Studio | Host profiles & application | Users apply to host; T&S approves; host badge | P4 | Must | Quality hosts | F52
F31 | Vent Studio | Shows & schedule | Recurring shows with episodes, follow a show, reminders | P4 | Must | Appointment listening | F30
F32 | Vent Studio | Live audio room | LiveKit room with host, co-host, on-air and listener roles | P4 | Must | RJ-style live show | F31
F33 | Vent Studio | Call-in queue | Listener raises hand with an 80-char topic; host brings one caller on air (8 min cap) | P4 | Must | Let it out live | F32
F34 | Vent Studio | Voice masking | Optional pitch-shift for callers | P6 | Could | Deeper anonymity | F33
F35 | Vent Studio | Reactions & text questions | Emoji reactions and anonymous text questions to the host | P4 | Should | Participate without speaking | F32
F36 | Vent Studio | On-air safety controls | Host drop/mute caller, auto-mute on report spike, no recording | P4 | Must | Safe live space | F32,F50
F40 | Travel Buddy | Commute plans | Recurring plan: from/to station, departure window, weekdays | P3 | Must | Set once, match daily | F04
F41 | Travel Buddy | Travel Now | Live intent: 'leaving Rajiv Chowk -> HUDA City Centre in 10 min'; expires in 45 min | P3 | Must | Spontaneous buddy | F04
F42 | Travel Buddy | Vibe match engine | Route overlap (station graph BFS) + time fit + vibe Jaccard + trust; hard filters | P3 | Must | Right person, right train | F40,F41,F03
F43 | Travel Buddy | Match request & accept | Both accept -> travel chat unlocked; expires automatically | P3 | Must | Consent first | F42,F23
F44 | Travel Buddy | Meet point | Station + platform + coach/door suggestion; women's coach aware; inside premises only | P3 | Must | Easy, safe meetup | F43
F45 | Travel Buddy | Trip lifecycle & feedback | Planned -> met -> completed / no-show / cancelled; private thumbs + safety flag | P3 | Must | Accountability | F43
F46 | Travel Buddy | Commute Crew | Matched people form a recurring crew group with a shared commute plan | P5 | Should | Daily travel squad | F45,F21
F47 | Travel Buddy | Matching preferences | Same gender only, verified only, age band, chatty/quiet | P3 | Must | Comfort and safety | F42
F50 | Safety | Report / block / mute | Available on every persona, post, comment, message, room and episode | P0 | Must | Control and store compliance | F02
F51 | Safety | Moderation queue | Admin console queue with case grouping, actions, appeals, audit | P1 | Must | Fast response to abuse | F50
F52 | Safety | Trust score & limits | Score from age, reports, feedback and verification; tiered rate limits | P5 | Should | Abuse resistance | F51
F53 | Safety | SOS & share trip | Trusted contacts get an SMS with station-level trip progress; SOS button on active trips | P3 | Must | Personal safety | F45
F54 | Safety | Safety center | Guidelines, helplines (112, Tele-MANAS 14416), how-to-report | P1 | Must | Know what to do
F55 | Safety | Grievance & appeals | IT Rules grievance officer flow with 24h ack / 15-day resolution, plus appeals | P1 | Must | Legal compliance | F51
F56 | Safety | Self-harm signal handling | Detect distress keywords -> show supportive helpline sheet; never punitive | P1 | Must | Care for vulnerable users | F24
F60 | Notifications | Push notifications | Expo push with categories and quiet hours | P2 | Must | Don't miss matches/replies | F01
F61 | Notifications | In-app inbox | Notification list with read state | P2 | Should | Catch up | F60
F70 | Platform | Admin console | React/Vite moderator console under /admin with RBAC | P1 | Must | Operate the platform | F51
F71 | Platform | Analytics | PII-free product events (signup funnel, D1/D7, matches, sessions) | P2 | Should | Learn what works
F72 | Platform | Data export & deletion | DPDP rights: export JSON, delete account within 30 days | P1 | Must | User rights | F01
F73 | Platform | Public site | Landing, privacy, terms, grievance officer, community guidelines (Go templates) | P1 | Must | Store listing requirements
F74 | Platform | Hindi i18n | Hindi + English UI, Hinglish-tolerant masker | P5 | Should | Reach more commuters
F80 | AI | AI moderation assist | Haiku triage of reports/UGC -> severity + reason; human decides | P5 | Should | Faster moderation | F51
F81 | AI | Icebreakers | 3 suggested openers on a new match based on shared vibes | P5 | Could | Break awkward silence | F43
F82 | AI | Host topic ideas | Suggested episode topics from trending bowl themes (no PII) | P5 | Could | Better shows | F31

## Tasks
Task ID | Phase | Feature ID | Layer | Task | Acceptance criteria | Priority | Est (days) | Depends on | Status | Owner
T001 | P0 |  | Infra | Monorepo: apps/mobile (Expo+TS+Router+NativeWind), server (Go+Echo), admin (Vite) | All three build locally with one command each | Must | 1 |  | Todo
T002 | P0 |  | Infra | Railway: API service, Postgres, Redis; env var schema | Health endpoint live on Railway with DB and Redis ping | Must | 1 | T001 | Todo
T003 | P0 |  | Infra | CI: go test, go vet, tsc, eslint, npm audit, govulncheck | PR fails on test/type/high-vuln errors | Must | 1 | T001 | Todo
T004 | P0 |  | Infra | EAS Build + EAS Update channels (dev/preview/prod) | Preview build installs on Android and iOS TestFlight | Must | 1 | T001 | Todo
T005 | P0 |  | Backend | DB layer: GORM, UUIDv7 base model, cursor pagination helper, migrations folder | Paginated list helper unit-tested | Must | 1 | T002 | Todo
T006 | P0 |  | Backend | Error envelope, request ID, structured logging with denylist, panic recovery | No stack traces or PII in responses or logs | Must | 1 | T005 | Todo
T007 | P0 |  | Backend | Redis rate limiter middleware (sliding window, keyed by ip/user/trust tier) | 429 returned past limit; limits configurable per route | Must | 1 | T002 | Todo
T010 | P0 | F01 | Backend | OTP request/verify with MSG91, HMAC phone hash, encrypted phone, throttling | 5 attempts max, 5 min TTL, per-number and per-IP throttles | Must | 2 | T007 | Todo
T011 | P0 | F01 | Backend | JWT access + rotating refresh tokens with family reuse detection | Reused refresh token revokes the family | Must | 2 | T010 | Todo
T012 | P0 | F01 | Mobile | Auth screens: phone entry, OTP entry, secure-store token handling, auto refresh | Cold start restores session; logout clears secure store | Must | 2 | T011 | Todo
T013 | P0 | F05 | Mobile | Age gate + itemised consent screen; consent records API | Cannot proceed without 18+ and core consent | Must | 1 | T012 | Todo
T014 | P0 | F02 | Backend | Persona service: alias generator, avatar seed, re-roll, alias history, 30-day change rule | Aliases unique per city; history kept | Must | 1 | T011 | Todo
T015 | P0 | F02 | Mobile | Persona creation screen with re-roll and generated avatar component | Avatar renders deterministically from seed | Must | 1 | T014 | Todo
T016 | P0 |  | Backend | Metro seed: cities, lines, stations, line_stations, interchange edges from GTFS (Delhi NCR first) | BFS returns correct path Rajiv Chowk -> HUDA City Centre | Must | 3 | T005 | Todo
T017 | P0 | F04 | Mobile | Station picker (search, line colour chips) + home metro setup screen | Search by name in under 100ms on device | Must | 1 | T016 | Todo
T018 | P0 | F03 | Backend | Vibe tag catalog + persona vibes + intents API | 3-10 tags enforced | Must | 1 | T014 | Todo
T019 | P0 | F03 | Mobile | Vibe picker screen | Selections saved and editable from profile | Must | 1 | T018 | Todo
T020 | P0 | F50 | Backend | Blocks, mutes, reports tables and APIs; excludeBlocked scope helper | Blocked personas invisible both ways in every list endpoint | Must | 2 | T014 | Todo
T021 | P0 | F50 | Mobile | Reusable report/block/mute action sheet | Reachable from profile, post, comment, message | Must | 1 | T020 | Todo
T022 | P0 |  | Mobile | App shell: tabs (Bowls, Chats, Travel, Studio, Me), theme, typed API client, TanStack Query setup | Tabs navigate; API errors show toast | Must | 1 | T012 | Todo
T030 | P1 | F24 | Backend | PII masker package: Indian phone, email, UPI, Aadhaar (Verhoeff), PAN, handles, URLs; table-driven tests | >=95% recall on test corpus incl. spaced/dashed numbers | Must | 3 | T005 | Todo
T031 | P1 | F24 | Backend | PII vault: AES-GCM encrypted raw text, 90-day TTL purge job, audited access | Purge job deletes expired rows; access writes audit log | Must | 1 | T030 | Todo
T032 | P1 | F24 | Backend | Async LLM second pass (Haiku) for obfuscated PII; emits update event | Spelled-out number gets masked and clients update | Should | 2 | T030 | Todo
T033 | P1 | F10 | Backend | Bowls: CRUD (admin), membership, suggestions by line/station/hub/college | New user sees line + station + city bowls suggested | Must | 2 | T016 | Todo
T034 | P1 | F11 | Backend | Posts API: text/image/poll, flair, masked body, R2 pre-signed upload, EXIF strip | Post body never stored unmasked | Must | 3 | T030,T033 | Todo
T035 | P1 | F12 | Backend | Comments (2 levels) + votes with denormalised counters | Vote idempotent per persona | Must | 2 | T034 | Todo
T036 | P1 | F13 | Backend | Feed endpoints Hot/New/Top; hot score cron every 5 min; cursor pagination | p95 feed latency < 200ms on 100k posts | Must | 2 | T035 | Todo
T037 | P1 | F10 | Mobile | Bowls tab: discover, joined list, bowl screen | Join/leave reflects immediately | Must | 2 | T033 | Todo
T038 | P1 | F11 | Mobile | Composer: text, image, poll, flair; PII preview warning | User sees masked preview before posting | Must | 2 | T034 | Todo
T039 | P1 | F12 | Mobile | Post detail with threaded comments, votes, OP badge | FlashList renders 500 comments smoothly | Must | 2 | T035 | Todo
T040 | P1 | F15 | Backend | Daily prompt scheduler per city + pinned prompt post | One prompt per city per day | Should | 1 | T034 | Todo
T041 | P1 | F70 | Admin | Admin console shell, RBAC (moderator, ts_lead, admin), login | Moderators cannot access vault | Must | 2 | T011 | Todo
T042 | P1 | F51 | Admin | Moderation queue: cases, content preview, actions (remove, warn, suspend, ban), audit | Every action writes moderation_action + audit_log | Must | 3 | T041,T020 | Todo
T043 | P1 | F55 | Backend | Grievance tickets + appeals with SLA timers | Ack within 24h tracked; overdue alerts | Must | 1 | T042 | Todo
T044 | P1 | F54 | Mobile | Safety center screens + helplines | Accessible from Me tab and every report sheet | Must | 1 | T022 | Todo
T045 | P1 | F56 | Backend | Distress keyword detector -> support sheet event (non-punitive) | Triggers helpline sheet, never a moderation action | Must | 1 | T030 | Todo
T046 | P1 | F72 | Backend | Data export job (JSON) + account deletion with 30-day grace | Deleted account's personas show as '[deleted]' | Must | 2 | T014 | Todo
T047 | P1 | F73 | Backend | Public pages: landing, privacy, terms, guidelines, grievance officer | Pages served from Go templates, indexed | Must | 1 | T002 | Todo
T050 | P2 | F23 | Backend | WS gateway: ticket auth, connection registry, Redis pub/sub fan-out, heartbeats | Message reaches recipient on another instance < 300ms | Must | 3 | T011 | Todo
T051 | P2 | F23 | Backend | Conversations + messages API, client message IDs (idempotent), cursor history | Duplicate send with same client id stored once | Must | 2 | T050,T030 | Todo
T052 | P2 | F23 | Backend | Typing, delivery/read receipts, presence (Redis TTL) | Receipts update in realtime | Should | 1 | T050 | Todo
T053 | P2 | F20 | Backend | DM requests: create/accept/ignore, daily limits by trust tier | Cannot message before acceptance | Must | 1 | T051 | Todo
T054 | P2 | F21 | Backend | Group chats: create, invite link, roles, member cap 50 | Non-members get 404 on group resources | Must | 2 | T051 | Todo
T055 | P2 | F22 | Backend | Discussion rooms: schedule, open/close, slow mode, bowl link | Room auto-closes at end time | Should | 2 | T051 | Todo
T056 | P2 | F23 | Mobile | WS client with reconnect/backoff, offline queue, optimistic send | Messages sent offline deliver on reconnect | Must | 3 | T050 | Todo
T057 | P2 | F20 | Mobile | Chats tab: requests, conversations list, chat screen | Unread counts accurate | Must | 3 | T053,T056 | Todo
T058 | P2 | F21 | Mobile | Group create/manage screens | Admin can remove members | Must | 2 | T054 | Todo
T059 | P2 | F22 | Mobile | Live rooms list + room screen | Join live room from bowl | Should | 2 | T055 | Todo
T060 | P2 | F60 | Backend | Push service: device tokens, Expo push, categories, quiet hours | No push during quiet hours except SOS | Must | 1 | T051 | Todo
T061 | P2 | F61 | Mobile | Notification inbox + permission prompt flow | Deep link opens target screen | Should | 1 | T060 | Todo
T062 | P2 | F71 | Backend | Analytics events endpoint (PII-free schema) | No persona/user ids in raw events, only hashed session | Should | 1 | T006 | Todo
T070 | P3 | F40 | Backend | Commute plans API + route path cache (station sequence) | Path stored on save | Must | 1 | T016 | Todo
T071 | P3 | F41 | Backend | Travel intents with 45-min TTL, Redis geo-less active index by line | Expired intents never matched | Must | 1 | T070 | Todo
T072 | P3 | F42 | Backend | Match engine: hard filters, overlap, time fit, vibe Jaccard, top-10, why-chips | Unit tests for scoring; blocked pairs never matched | Must | 3 | T071,T018,T020 | Todo
T073 | P3 | F43 | Backend | Match requests/accept -> creates travel conversation; expiry | Chat exists only after both accept | Must | 1 | T072,T051 | Todo
T074 | P3 | F44 | Backend | Meet point suggestion (station, platform, coach) with women's coach rule | Meet point always inside station | Must | 1 | T073 | Todo
T075 | P3 | F45 | Backend | Trips: lifecycle, check-in, no-show, feedback, safety flag -> moderation case | Safety flag opens a T&S case | Must | 2 | T073 | Todo
T076 | P3 | F47 | Backend | Matching preferences (gender, verified, age band) | Filters applied before scoring | Must | 1 | T072 | Todo
T077 | P3 | F53 | Backend | Trusted contacts, share-trip link, SOS SMS + T&S alert | SOS reaches contacts < 30s | Must | 2 | T075 | Todo
T078 | P3 | F40 | Mobile | Travel tab: commute plans, Travel Now | Plan editable; Travel Now shows countdown | Must | 2 | T070,T071 | Todo
T079 | P3 | F42 | Mobile | Match cards with why-chips, request/accept | Never shows home station | Must | 2 | T072,T073 | Todo
T080 | P3 | F45 | Mobile | Trip screen: meet point, check-in, share trip, SOS, feedback | SOS reachable in 1 tap on active trip | Must | 2 | T075,T077 | Todo
T081 | P3 |  | Infra | Launch checklist: store listings, privacy labels, UGC compliance, load test | Both stores approve | Must | 3 | T080 | Todo
T090 | P4 | F30 | Backend | Host applications + host profile + approval in admin | Only approved hosts create shows | Must | 1 | T042 | Todo
T091 | P4 | F31 | Backend | Shows, episodes, follows, reminders | Followers get push 10 min before episode | Must | 2 | T090,T060 | Todo
T092 | P4 | F32 | Backend | LiveKit integration: room per episode, role-based tokens, webhooks | Listener token cannot publish audio | Must | 3 | T091 | Todo
T093 | P4 | F33 | Backend | Call-in queue, stage/unstage, 8-min cap, token revoke on drop | Dropped caller loses publish within 2s | Must | 2 | T092 | Todo
T094 | P4 | F35 | Backend | Reactions + text questions (masked) over WS | Questions pass PII masker | Should | 1 | T092,T030 | Todo
T095 | P4 | F36 | Backend | Episode safety: report spike auto-mute, host controls, no recording enforced | Auto-mute triggers at threshold | Must | 1 | T093 | Todo
T096 | P4 | F31 | Mobile | Studio tab: schedule, live now, show page, follow | Live now shows listener count | Must | 2 | T091 | Todo
T097 | P4 | F32 | Mobile | Live room UI: stage, listeners, raise hand, reactions, questions | Audio continues with screen locked | Must | 3 | T092,T093 | Todo
T098 | P4 | F33 | Mobile | Host controls: queue, bring on air, drop, timer | Host sees caller topic before staging | Must | 2 | T093 | Todo
T100 | P5 | F46 | Backend | Commute crews: crew from accepted matches, shared plan, group chat | Crew max 6 members | Should | 2 | T075,T054 | Todo
T101 | P5 | F08 | Backend | Reveal ladder per conversation; lifts masking for contact level | Requires both consents per level | Should | 2 | T051 | Todo
T102 | P5 | F52 | Backend | Trust score computation + tiered limits | Score recomputed nightly and on events | Should | 2 | T042 | Todo
T103 | P5 | F14 | Backend | User-created bowls + bowl moderator tools | Requires trust tier >= 2 | Should | 2 | T102 | Todo
T104 | P5 | F80 | Backend | AI triage of reports (Haiku), severity + rationale on case | Suggestion only; no auto action | Should | 2 | T042 | Todo
T105 | P5 | F81 | Backend | Icebreakers (Sonnet) on new match from shared vibes | No PII in prompt; per-user daily cap | Could | 1 | T073 | Todo
T106 | P5 | F82 | Backend | Host topic ideas from trending bowl themes | Uses aggregated, masked text only | Could | 1 | T091 | Todo
T107 | P5 | F74 | Mobile | i18n (en, hi) with expo-localization | All strings externalised | Should | 2 | T022 | Todo
T108 | P5 | F26 | Backend | Disappearing messages TTL purge | Messages deleted server-side after TTL | Could | 1 | T051 | Todo
T109 | P5 | F25 | Backend | Chat images + NSFW gate | Image hidden until scan passes | Could | 2 | T051 | Todo
T110 | P6 | F07 | Backend | Selfie liveness verification via vendor; store boolean only | No face image retained | Could | 3 | T014 | Todo
T111 | P6 | F34 | Mobile | Caller voice masking (pitch shift track processor) | Toggle before going on air | Could | 3 | T097 | Todo
T112 | P6 | F06 | Backend | Play Integrity / App Attest at signup | Failed attestation -> stricter limits, not hard block | Could | 2 | T010 | Todo

## Phase Summary
Phase | Name | Tasks | Est (days) | Done | % done
P0 | Foundation
P1 | Bowls
P2 | Chat & discussion
P3 | Travel Buddy (MVP launch)
P4 | Vent Studio
P5 | Trust & growth
P6 | Later
Total

## Entities
Entity | Domain | Description | Retention | Field count
User | Identity | Private account. Never exposed to other users. | Until deletion + 30 days | 15
Persona | Identity | Public anonymous face. All social objects point here. | Tombstoned on user deletion | 13
PersonaAliasHistory | Identity | Old aliases for moderation lookups. | Life of account | 5
Device | Identity | Install with push token. | 90 days after last seen | 9
RefreshToken | Identity | Rotating refresh tokens (hashed). | Expiry + 7 days | 8
Consent | Identity | DPDP itemised consent records (append-only). | Life of account + 3 years | 6
TrustedContact | Identity | SOS / share-trip recipients. | Until removed | 6
UserSettings | Identity | Per-user preferences. | Life of account | 9
City | Metro | Metro city. | Reference | 4
MetroLine | Metro | Line within a city. | Reference | 5
Station | Metro | Metro station. | Reference | 8
LineStation | Metro | Ordered station on a line (graph edges = consecutive seq). | Reference | 4
VibeTag | Vibe | Catalog of vibe tags. | Reference | 5
PersonaVibe | Vibe | Persona <-> VibeTag (3-10 per persona). | Life of persona | 2
Bowl | Community | Fishbowl-style community. | Life of platform | 15
BowlMember | Community | Membership + role. | Until leave | 5
Post | Community | Anonymous post in a bowl. | Until deleted; 30 days soft | 17
Poll | Community | Poll attached to a post. | With post | 3
PollOption | Community | Poll option. | With post | 4
PollVote | Community | One per persona per option. | With post | 2
Comment | Community | Threaded comment (max depth 2). | Until deleted; 30 days soft | 11
Vote | Community | Up/down vote on post or comment. | With target | 4
Conversation | Messaging | DM, group, crew, travel or discussion room. | Until all members leave + 30 days | 16
ConversationMember | Messaging | Membership + read state. | With conversation | 8
DmRequest | Messaging | Consent gate for 1:1 chat. | 90 days | 10
Message | Messaging | Chat message (masked). | Until deleted or TTL | 12
PiiVault | Safety | Encrypted raw UGC for legal requests only. | 90 days TTL, then hard delete | 6
PiiDetection | Safety | What was masked (no raw values). | 1 year | 6
CommutePlan | Travel | Recurring commute. | Until removed | 12
TravelIntent | Travel | Live 'Travel Now' or a day's instance of a plan. | 7 days | 12
Match | Travel | Candidate pairing between two intents. | 90 days | 15
Trip | Travel | Accepted match turned into a meet-up. | 1 year | 11
TripParticipant | Travel | Who is on the trip + check-in. | 1 year | 4
TripFeedback | Travel | Private feedback after trip. | 2 years | 10
Crew | Travel | Recurring commute squad. | Until disbanded | 9
SosEvent | Safety | SOS trigger. | 3 years | 8
HostProfile | Studio | Approved RJ host. | Life of persona | 7
Show | Studio | Recurring live audio show. | Life of platform | 10
ShowFollower | Studio | Follow for reminders. | Until unfollow | 2
ShowEpisode | Studio | One live session. | 1 year metadata, no audio | 11
EpisodeParticipant | Studio | Role in a live episode. | 1 year | 5
CallInRequest | Studio | Raise-hand to go on air. | 1 year | 10
Report | Safety | User report on any content or persona. | 3 years | 9
Block | Safety | Bidirectional invisibility. | Until unblocked | 4
Mute | Safety | One-way hide. | Until unmuted | 3
ModerationCase | Safety | Grouped reports on one target. | 3 years | 11
ModerationAction | Safety | Action taken by a human. | 5 years | 9
Appeal | Safety | User appeal against action. | 5 years | 8
GrievanceTicket | Safety | IT Rules grievance. | 5 years | 10
TrustEvent | Safety | Inputs to trust score. | 2 years | 6
RevealEvent | Messaging | Consent log for reveal ladder. | Life of conversation | 6
Notification | Notify | In-app inbox item. | 60 days | 6
AdminUser | System | Moderator / staff account (separate from User). | Employment + 1 year | 7
AuditLog | System | Append-only log of privileged reads/writes. | 5 years | 8
SecurityEvent | System | Failed logins, OTP abuse, permission denials, rate-limit trips. | 1 year | 6
AiUsage | System | Per-call AI cost tracking. | 2 years | 8

## Fields
Entity | Domain | Field | Type | Constraints | Privacy class | Note
User | Identity | id | uuid v7 | PK | P0
User | Identity | created_at | timestamptz | not null | P0
User | Identity | updated_at | timestamptz | not null | P0
User | Identity | deleted_at | timestamptz | nullable, index | P0 | soft delete
User | Identity | phone_hash | bytea | unique, not null | P3 | HMAC-SHA256(pepper, E.164)
User | Identity | phone_enc | bytea | not null | P3 | AES-GCM; used only for SMS
User | Identity | status | enum user_status | not null, index | P0
User | Identity | birth_year | smallint | not null | P2 | 18+ check; age band derived
User | Identity | gender | enum gender | nullable | P2 | self-declared; for matching filters only
User | Identity | city_id | uuid | FK City | P2
User | Identity | verified_at | timestamptz | nullable | P2 | selfie liveness passed
User | Identity | trust_score | int | default 50 | P2 | 0-100
User | Identity | trust_tier | smallint | default 0, index | P2 | derived from score
User | Identity | locale | varchar(8) | default 'en' | P2
User | Identity | last_active_at | timestamptz | index | P2
Persona | Identity | id | uuid v7 | PK | P0
Persona | Identity | created_at | timestamptz | not null | P0
Persona | Identity | updated_at | timestamptz | not null | P0
Persona | Identity | deleted_at | timestamptz | nullable, index | P0 | soft delete
Persona | Identity | user_id | uuid | FK User, unique | P3 | never serialized to other clients
Persona | Identity | alias | varchar(40) | unique per city | P1
Persona | Identity | avatar_seed | varchar(32) | not null | P1
Persona | Identity | bio | varchar(160) | masked | P1
Persona | Identity | alias_changed_at | timestamptz | nullable | P0 | 30-day rule
Persona | Identity | home_station_id | uuid | FK Station | P2 | never shown to others
Persona | Identity | work_station_id | uuid | FK Station | P2 | never shown to others
Persona | Identity | intents | text[] | enum persona_intent values | P1
Persona | Identity | is_host | bool | default false | P1
PersonaAliasHistory | Identity | id | uuid v7 | PK | P0
PersonaAliasHistory | Identity | persona_id | uuid | FK Persona, index | P1
PersonaAliasHistory | Identity | alias | varchar(40) |  | P1
PersonaAliasHistory | Identity | used_from | timestamptz |  | P0
PersonaAliasHistory | Identity | used_to | timestamptz |  | P0
Device | Identity | id | uuid v7 | PK | P0
Device | Identity | created_at | timestamptz | not null | P0
Device | Identity | updated_at | timestamptz | not null | P0
Device | Identity | user_id | uuid | FK User, index | P3
Device | Identity | platform | enum platform |  | P0
Device | Identity | push_token | text | nullable | P2
Device | Identity | app_version | varchar(16) |  | P0
Device | Identity | attestation_ok | bool | nullable | P0
Device | Identity | last_seen_at | timestamptz |  | P0
RefreshToken | Identity | id | uuid v7 | PK | P0
RefreshToken | Identity | user_id | uuid | FK User, index | P3
RefreshToken | Identity | device_id | uuid | FK Device | P0
RefreshToken | Identity | family_id | uuid | index | P0 | revoke whole family on reuse
RefreshToken | Identity | token_hash | bytea | unique | P3
RefreshToken | Identity | expires_at | timestamptz |  | P0
RefreshToken | Identity | revoked_at | timestamptz | nullable | P0
RefreshToken | Identity | replaced_by | uuid | nullable | P0
Consent | Identity | id | uuid v7 | PK | P0
Consent | Identity | user_id | uuid | FK User, index | P3
Consent | Identity | purpose | enum consent_purpose |  | P0
Consent | Identity | granted | bool |  | P0
Consent | Identity | policy_version | varchar(16) |  | P0
Consent | Identity | created_at | timestamptz |  | P0
TrustedContact | Identity | id | uuid v7 | PK | P0
TrustedContact | Identity | created_at | timestamptz | not null | P0
TrustedContact | Identity | updated_at | timestamptz | not null | P0
TrustedContact | Identity | user_id | uuid | FK User, index | P3
TrustedContact | Identity | name | varchar(60) |  | P2
TrustedContact | Identity | phone_enc | bytea |  | P3
UserSettings | Identity | user_id | uuid | PK, FK User | P3
UserSettings | Identity | match_same_gender_only | bool | default false | P2
UserSettings | Identity | match_verified_only | bool | default false | P2
UserSettings | Identity | match_age_min | smallint |  | P2
UserSettings | Identity | match_age_max | smallint |  | P2
UserSettings | Identity | quiet_hours_start | time | nullable | P2
UserSettings | Identity | quiet_hours_end | time | nullable | P2
UserSettings | Identity | dm_from | enum dm_policy | default 'requests' | P2
UserSettings | Identity | notif_prefs | jsonb |  | P2
City | Metro | id | uuid v7 | PK | P0
City | Metro | name | varchar(40) | unique | P0
City | Metro | code | varchar(8) | unique | P0 | DEL, MUM, BLR
City | Metro | is_live | bool |  | P0
MetroLine | Metro | id | uuid v7 | PK | P0
MetroLine | Metro | city_id | uuid | FK City, index | P0
MetroLine | Metro | name | varchar(40) |  | P0 | Yellow Line
MetroLine | Metro | color_hex | char(7) |  | P0
MetroLine | Metro | gtfs_route_id | varchar(32) |  | P0
Station | Metro | id | uuid v7 | PK | P0
Station | Metro | city_id | uuid | FK City, index | P0
Station | Metro | name | varchar(80) | index (trigram) | P0
Station | Metro | code | varchar(16) |  | P0
Station | Metro | lat | numeric(9,6) |  | P0 | station location, public
Station | Metro | lng | numeric(9,6) |  | P0
Station | Metro | is_interchange | bool |  | P0
Station | Metro | has_womens_coach_note | varchar(120) | nullable | P0
LineStation | Metro | line_id | uuid | PK part, FK MetroLine | P0
LineStation | Metro | station_id | uuid | PK part, FK Station | P0
LineStation | Metro | seq | smallint | not null | P0
LineStation | Metro | platform_hint | varchar(40) | nullable | P0
VibeTag | Vibe | id | uuid v7 | PK | P0
VibeTag | Vibe | slug | varchar(32) | unique | P0 | indie-music
VibeTag | Vibe | label_en | varchar(40) |  | P0
VibeTag | Vibe | label_hi | varchar(40) |  | P0
VibeTag | Vibe | category | enum vibe_category |  | P0
PersonaVibe | Vibe | persona_id | uuid | PK part, FK Persona | P1
PersonaVibe | Vibe | vibe_tag_id | uuid | PK part, FK VibeTag | P0
Bowl | Community | id | uuid v7 | PK | P0
Bowl | Community | created_at | timestamptz | not null | P0
Bowl | Community | updated_at | timestamptz | not null | P0
Bowl | Community | deleted_at | timestamptz | nullable, index | P0 | soft delete
Bowl | Community | city_id | uuid | FK City, nullable | P0 | null = national
Bowl | Community | kind | enum bowl_kind | index | P0
Bowl | Community | slug | varchar(48) | unique | P0
Bowl | Community | name | varchar(60) |  | P0
Bowl | Community | description | varchar(300) |  | P0
Bowl | Community | line_id | uuid | FK MetroLine, nullable | P0
Bowl | Community | station_id | uuid | FK Station, nullable | P0
Bowl | Community | visibility | enum bowl_visibility |  | P0
Bowl | Community | created_by_persona_id | uuid | FK Persona, nullable | P1
Bowl | Community | member_count | int | denormalised | P0
Bowl | Community | rules_md | text |  | P0
BowlMember | Community | bowl_id | uuid | PK part, FK Bowl | P0
BowlMember | Community | persona_id | uuid | PK part, FK Persona, index | P1
BowlMember | Community | role | enum bowl_role |  | P1
BowlMember | Community | joined_at | timestamptz |  | P0
BowlMember | Community | muted_until | timestamptz | nullable | P0
Post | Community | id | uuid v7 | PK | P0
Post | Community | created_at | timestamptz | not null | P0
Post | Community | updated_at | timestamptz | not null | P0
Post | Community | deleted_at | timestamptz | nullable, index | P0 | soft delete
Post | Community | bowl_id | uuid | FK Bowl, index | P0
Post | Community | author_persona_id | uuid | FK Persona, index | P1
Post | Community | type | enum post_type |  | P0
Post | Community | title | varchar(140) | masked | P1
Post | Community | body_masked | text | masked | P1
Post | Community | flair | varchar(24) | nullable | P0
Post | Community | media | jsonb | R2 keys + dims | P1
Post | Community | pii_flags | smallint | bitmask of masked kinds | P0
Post | Community | status | enum content_status | index | P0
Post | Community | score | int | denormalised | P0
Post | Community | comment_count | int | denormalised | P0
Post | Community | hot_rank | double | index | P0
Post | Community | is_prompt | bool |  | P0 | daily prompt
Poll | Community | post_id | uuid | PK, FK Post | P0
Poll | Community | closes_at | timestamptz |  | P0
Poll | Community | multi | bool |  | P0
PollOption | Community | id | uuid v7 | PK | P0
PollOption | Community | post_id | uuid | FK Poll | P0
PollOption | Community | label | varchar(60) | masked | P1
PollOption | Community | vote_count | int |  | P0
PollVote | Community | option_id | uuid | PK part | P0
PollVote | Community | persona_id | uuid | PK part | P1 | never shown
Comment | Community | id | uuid v7 | PK | P0
Comment | Community | created_at | timestamptz | not null | P0
Comment | Community | updated_at | timestamptz | not null | P0
Comment | Community | deleted_at | timestamptz | nullable, index | P0 | soft delete
Comment | Community | post_id | uuid | FK Post, index | P0
Comment | Community | parent_id | uuid | FK Comment, nullable | P0
Comment | Community | author_persona_id | uuid | FK Persona | P1
Comment | Community | body_masked | text | masked | P1
Comment | Community | depth | smallint | 0..2 | P0
Comment | Community | status | enum content_status |  | P0
Comment | Community | score | int |  | P0
Vote | Community | persona_id | uuid | PK part | P1 | never shown
Vote | Community | target_type | enum vote_target | PK part | P0
Vote | Community | target_id | uuid | PK part, index | P0
Vote | Community | value | smallint | -1 or 1 | P0
Conversation | Messaging | id | uuid v7 | PK | P0
Conversation | Messaging | created_at | timestamptz | not null | P0
Conversation | Messaging | updated_at | timestamptz | not null | P0
Conversation | Messaging | deleted_at | timestamptz | nullable, index | P0 | soft delete
Conversation | Messaging | kind | enum conversation_kind | index | P0
Conversation | Messaging | title | varchar(60) | nullable, masked | P1
Conversation | Messaging | bowl_id | uuid | FK Bowl, nullable | P0 | discussion rooms
Conversation | Messaging | match_id | uuid | FK Match, nullable | P0 | travel chats
Conversation | Messaging | crew_id | uuid | FK Crew, nullable | P0
Conversation | Messaging | starts_at | timestamptz | nullable | P0 | rooms
Conversation | Messaging | ends_at | timestamptz | nullable | P0 | rooms
Conversation | Messaging | slow_mode_sec | smallint | default 0 | P0
Conversation | Messaging | disappear_after_sec | int | nullable | P0
Conversation | Messaging | member_cap | smallint |  | P0
Conversation | Messaging | invite_code | varchar(16) | unique, nullable | P0
Conversation | Messaging | last_message_at | timestamptz | index | P0
ConversationMember | Messaging | conversation_id | uuid | PK part | P0
ConversationMember | Messaging | persona_id | uuid | PK part, index | P1
ConversationMember | Messaging | role | enum conv_role |  | P1
ConversationMember | Messaging | last_read_message_id | uuid | nullable | P1
ConversationMember | Messaging | muted_until | timestamptz | nullable | P0
ConversationMember | Messaging | reveal_level | enum reveal_level | default 'none' | P1 | what I agreed to reveal
ConversationMember | Messaging | joined_at | timestamptz |  | P0
ConversationMember | Messaging | left_at | timestamptz | nullable | P0
DmRequest | Messaging | id | uuid v7 | PK | P0
DmRequest | Messaging | created_at | timestamptz | not null | P0
DmRequest | Messaging | updated_at | timestamptz | not null | P0
DmRequest | Messaging | from_persona_id | uuid | FK Persona, index | P1
DmRequest | Messaging | to_persona_id | uuid | FK Persona, index | P1
DmRequest | Messaging | intro_masked | varchar(200) | masked | P1
DmRequest | Messaging | context_type | enum dm_context |  | P0 | post/comment/room
DmRequest | Messaging | context_id | uuid | nullable | P0
DmRequest | Messaging | status | enum request_status |  | P0
DmRequest | Messaging | conversation_id | uuid | nullable | P0
Message | Messaging | id | uuid v7 | PK (client-generated, idempotent) | P0
Message | Messaging | conversation_id | uuid | FK, index (conv, id) | P0
Message | Messaging | sender_persona_id | uuid | FK Persona | P1
Message | Messaging | kind | enum message_kind |  | P0
Message | Messaging | body_masked | text | masked | P1
Message | Messaging | media | jsonb | nullable | P1
Message | Messaging | reply_to_id | uuid | nullable | P0
Message | Messaging | pii_flags | smallint |  | P0
Message | Messaging | status | enum content_status |  | P0
Message | Messaging | created_at | timestamptz |  | P0
Message | Messaging | edited_at | timestamptz | nullable | P0
Message | Messaging | expires_at | timestamptz | nullable, index | P0
PiiVault | Safety | id | uuid v7 | PK | P0
PiiVault | Safety | content_type | enum content_type |  | P0
PiiVault | Safety | content_id | uuid | index | P0
PiiVault | Safety | raw_enc | bytea | AES-GCM | P3
PiiVault | Safety | key_version | smallint |  | P0
PiiVault | Safety | expires_at | timestamptz | index | P0
PiiDetection | Safety | id | uuid v7 | PK | P0
PiiDetection | Safety | content_type | enum content_type |  | P0
PiiDetection | Safety | content_id | uuid | index | P0
PiiDetection | Safety | kind | enum pii_kind |  | P0
PiiDetection | Safety | source | enum detector | regex/llm | P0
PiiDetection | Safety | created_at | timestamptz |  | P0
CommutePlan | Travel | id | uuid v7 | PK | P0
CommutePlan | Travel | created_at | timestamptz | not null | P0
CommutePlan | Travel | updated_at | timestamptz | not null | P0
CommutePlan | Travel | deleted_at | timestamptz | nullable, index | P0 | soft delete
CommutePlan | Travel | persona_id | uuid | FK Persona, index | P2
CommutePlan | Travel | from_station_id | uuid | FK Station | P2
CommutePlan | Travel | to_station_id | uuid | FK Station | P2
CommutePlan | Travel | depart_window_start | time |  | P2
CommutePlan | Travel | depart_window_end | time |  | P2
CommutePlan | Travel | weekdays | smallint | bitmask Mon..Sun | P2
CommutePlan | Travel | path_station_ids | uuid[] | cached BFS path | P2
CommutePlan | Travel | active | bool | index | P0
TravelIntent | Travel | id | uuid v7 | PK | P0
TravelIntent | Travel | created_at | timestamptz | not null | P0
TravelIntent | Travel | updated_at | timestamptz | not null | P0
TravelIntent | Travel | persona_id | uuid | FK Persona, index | P2
TravelIntent | Travel | commute_plan_id | uuid | FK CommutePlan, nullable | P2
TravelIntent | Travel | from_station_id | uuid | FK Station | P2
TravelIntent | Travel | to_station_id | uuid | FK Station | P2
TravelIntent | Travel | depart_at | timestamptz | index | P2
TravelIntent | Travel | expires_at | timestamptz | index | P0
TravelIntent | Travel | path_station_ids | uuid[] |  | P2
TravelIntent | Travel | mood | enum travel_mood | chatty/quiet/either | P1
TravelIntent | Travel | status | enum intent_status |  | P0
Match | Travel | id | uuid v7 | PK | P0
Match | Travel | created_at | timestamptz | not null | P0
Match | Travel | updated_at | timestamptz | not null | P0
Match | Travel | intent_a_id | uuid | FK TravelIntent | P0
Match | Travel | intent_b_id | uuid | FK TravelIntent | P0
Match | Travel | persona_a_id | uuid | FK Persona, index | P1
Match | Travel | persona_b_id | uuid | FK Persona, index | P1
Match | Travel | score | numeric(4,3) |  | P0
Match | Travel | why | jsonb | chips | P1
Match | Travel | overlap_from_station_id | uuid |  | P1 | only shared segment exposed
Match | Travel | overlap_to_station_id | uuid |  | P1
Match | Travel | a_status | enum match_side_status |  | P0
Match | Travel | b_status | enum match_side_status |  | P0
Match | Travel | status | enum match_status | index | P0
Match | Travel | expires_at | timestamptz |  | P0
Trip | Travel | id | uuid v7 | PK | P0
Trip | Travel | created_at | timestamptz | not null | P0
Trip | Travel | updated_at | timestamptz | not null | P0
Trip | Travel | match_id | uuid | FK Match, unique | P0
Trip | Travel | crew_id | uuid | FK Crew, nullable | P0
Trip | Travel | meet_station_id | uuid | FK Station | P1
Trip | Travel | meet_platform | varchar(40) |  | P1
Trip | Travel | meet_coach | varchar(20) |  | P1 | e.g. Coach 3, Door 2
Trip | Travel | meet_at | timestamptz |  | P1
Trip | Travel | status | enum trip_status | index | P0
Trip | Travel | share_token | varchar(32) | unique, nullable | P2 | share-trip link
TripParticipant | Travel | trip_id | uuid | PK part | P0
TripParticipant | Travel | persona_id | uuid | PK part | P1
TripParticipant | Travel | checked_in_at | timestamptz | nullable | P2
TripParticipant | Travel | no_show | bool | default false | P0
TripFeedback | Travel | id | uuid v7 | PK | P0
TripFeedback | Travel | created_at | timestamptz | not null | P0
TripFeedback | Travel | updated_at | timestamptz | not null | P0
TripFeedback | Travel | trip_id | uuid | FK Trip | P0
TripFeedback | Travel | from_persona_id | uuid |  | P1
TripFeedback | Travel | to_persona_id | uuid |  | P1
TripFeedback | Travel | thumbs | smallint | -1/1 | P2 | never shown
TripFeedback | Travel | felt_safe | bool |  | P2
TripFeedback | Travel | safety_flag | bool | opens case | P2
TripFeedback | Travel | note_masked | varchar(300) |  | P2
Crew | Travel | id | uuid v7 | PK | P0
Crew | Travel | created_at | timestamptz | not null | P0
Crew | Travel | updated_at | timestamptz | not null | P0
Crew | Travel | deleted_at | timestamptz | nullable, index | P0 | soft delete
Crew | Travel | name | varchar(40) | masked | P1
Crew | Travel | line_id | uuid | FK MetroLine | P1
Crew | Travel | depart_window_start | time |  | P1
Crew | Travel | weekdays | smallint |  | P1
Crew | Travel | member_cap | smallint | default 6 | P0
SosEvent | Safety | id | uuid v7 | PK | P0
SosEvent | Safety | created_at | timestamptz | not null | P0
SosEvent | Safety | updated_at | timestamptz | not null | P0
SosEvent | Safety | user_id | uuid | FK User | P3
SosEvent | Safety | trip_id | uuid | FK Trip, nullable | P0
SosEvent | Safety | last_station_id | uuid | nullable | P2
SosEvent | Safety | status | enum sos_status |  | P0
SosEvent | Safety | resolved_by | uuid | admin, nullable | P0
HostProfile | Studio | id | uuid v7 | PK | P0
HostProfile | Studio | created_at | timestamptz | not null | P0
HostProfile | Studio | updated_at | timestamptz | not null | P0
HostProfile | Studio | persona_id | uuid | FK Persona, unique | P1
HostProfile | Studio | status | enum host_status |  | P0
HostProfile | Studio | tagline | varchar(80) |  | P1
HostProfile | Studio | approved_by | uuid | admin, nullable | P0
Show | Studio | id | uuid v7 | PK | P0
Show | Studio | created_at | timestamptz | not null | P0
Show | Studio | updated_at | timestamptz | not null | P0
Show | Studio | deleted_at | timestamptz | nullable, index | P0 | soft delete
Show | Studio | host_persona_id | uuid | FK Persona, index | P1
Show | Studio | city_id | uuid | FK City, nullable | P0
Show | Studio | title | varchar(60) |  | P1
Show | Studio | description | varchar(300) |  | P1
Show | Studio | topic_tags | text[] |  | P0
Show | Studio | schedule_rrule | varchar(120) | nullable | P0
ShowFollower | Studio | show_id | uuid | PK part | P0
ShowFollower | Studio | persona_id | uuid | PK part | P1
ShowEpisode | Studio | id | uuid v7 | PK | P0
ShowEpisode | Studio | created_at | timestamptz | not null | P0
ShowEpisode | Studio | updated_at | timestamptz | not null | P0
ShowEpisode | Studio | show_id | uuid | FK Show, index | P0
ShowEpisode | Studio | title | varchar(80) |  | P1
ShowEpisode | Studio | scheduled_at | timestamptz | index | P0
ShowEpisode | Studio | started_at | timestamptz | nullable | P0
ShowEpisode | Studio | ended_at | timestamptz | nullable | P0
ShowEpisode | Studio | status | enum episode_status |  | P0
ShowEpisode | Studio | livekit_room | varchar(64) |  | P0
ShowEpisode | Studio | peak_listeners | int |  | P0
EpisodeParticipant | Studio | episode_id | uuid | PK part | P0
EpisodeParticipant | Studio | persona_id | uuid | PK part | P1
EpisodeParticipant | Studio | role | enum stage_role |  | P1
EpisodeParticipant | Studio | joined_at | timestamptz |  | P0
EpisodeParticipant | Studio | left_at | timestamptz | nullable | P0
CallInRequest | Studio | id | uuid v7 | PK | P0
CallInRequest | Studio | created_at | timestamptz | not null | P0
CallInRequest | Studio | updated_at | timestamptz | not null | P0
CallInRequest | Studio | episode_id | uuid | FK ShowEpisode, index | P0
CallInRequest | Studio | persona_id | uuid | FK Persona | P1
CallInRequest | Studio | topic_masked | varchar(80) | masked | P1
CallInRequest | Studio | status | enum callin_status |  | P0
CallInRequest | Studio | on_air_at | timestamptz | nullable | P0
CallInRequest | Studio | off_air_at | timestamptz | nullable | P0
CallInRequest | Studio | voice_masked | bool |  | P1
Report | Safety | id | uuid v7 | PK | P0
Report | Safety | created_at | timestamptz | not null | P0
Report | Safety | updated_at | timestamptz | not null | P0
Report | Safety | reporter_persona_id | uuid | FK Persona | P1 | hidden from target
Report | Safety | target_type | enum content_type | index | P0
Report | Safety | target_id | uuid | index | P0
Report | Safety | reason | enum report_reason |  | P0
Report | Safety | details_masked | varchar(500) |  | P2
Report | Safety | case_id | uuid | FK ModerationCase | P0
Block | Safety | blocker_persona_id | uuid | PK part | P1
Block | Safety | blocked_persona_id | uuid | PK part, index | P1
Block | Safety | blocker_user_id | uuid | index | P3 | blocks follow the human across alias changes
Block | Safety | created_at | timestamptz |  | P0
Mute | Safety | muter_persona_id | uuid | PK part | P1
Mute | Safety | muted_persona_id | uuid | PK part | P1
Mute | Safety | created_at | timestamptz |  | P0
ModerationCase | Safety | id | uuid v7 | PK | P0
ModerationCase | Safety | created_at | timestamptz | not null | P0
ModerationCase | Safety | updated_at | timestamptz | not null | P0
ModerationCase | Safety | target_type | enum content_type |  | P0
ModerationCase | Safety | target_id | uuid | index | P0
ModerationCase | Safety | severity | enum severity | index | P0
ModerationCase | Safety | ai_severity | enum severity | nullable | P0 | suggestion only
ModerationCase | Safety | ai_rationale | text | nullable | P0
ModerationCase | Safety | status | enum case_status | index | P0
ModerationCase | Safety | assignee_admin_id | uuid | nullable | P0
ModerationCase | Safety | sla_due_at | timestamptz | index | P0
ModerationAction | Safety | id | uuid v7 | PK | P0
ModerationAction | Safety | created_at | timestamptz | not null | P0
ModerationAction | Safety | updated_at | timestamptz | not null | P0
ModerationAction | Safety | case_id | uuid | FK ModerationCase | P0
ModerationAction | Safety | admin_id | uuid | FK AdminUser | P0
ModerationAction | Safety | action | enum mod_action |  | P0
ModerationAction | Safety | target_user_id | uuid | nullable | P3
ModerationAction | Safety | until | timestamptz | nullable | P0
ModerationAction | Safety | note | text |  | P0
Appeal | Safety | id | uuid v7 | PK | P0
Appeal | Safety | created_at | timestamptz | not null | P0
Appeal | Safety | updated_at | timestamptz | not null | P0
Appeal | Safety | action_id | uuid | FK ModerationAction | P0
Appeal | Safety | user_id | uuid | FK User | P3
Appeal | Safety | text_masked | varchar(1000) |  | P2
Appeal | Safety | status | enum appeal_status |  | P0
Appeal | Safety | decided_by | uuid | nullable | P0
GrievanceTicket | Safety | id | uuid v7 | PK | P0
GrievanceTicket | Safety | created_at | timestamptz | not null | P0
GrievanceTicket | Safety | updated_at | timestamptz | not null | P0
GrievanceTicket | Safety | user_id | uuid | nullable | P3
GrievanceTicket | Safety | contact_email_enc | bytea | nullable | P3 | non-user complainants
GrievanceTicket | Safety | category | enum grievance_category |  | P0
GrievanceTicket | Safety | body_enc | bytea |  | P3
GrievanceTicket | Safety | acknowledged_at | timestamptz | nullable | P0
GrievanceTicket | Safety | resolved_at | timestamptz | nullable | P0
GrievanceTicket | Safety | status | enum case_status |  | P0
TrustEvent | Safety | id | uuid v7 | PK | P0
TrustEvent | Safety | user_id | uuid | FK User, index | P3
TrustEvent | Safety | kind | enum trust_event_kind |  | P0
TrustEvent | Safety | delta | smallint |  | P0
TrustEvent | Safety | ref_id | uuid | nullable | P0
TrustEvent | Safety | created_at | timestamptz |  | P0
RevealEvent | Messaging | id | uuid v7 | PK | P0
RevealEvent | Messaging | conversation_id | uuid | index | P0
RevealEvent | Messaging | persona_id | uuid |  | P1
RevealEvent | Messaging | level | enum reveal_level |  | P0
RevealEvent | Messaging | action | enum reveal_action | grant/revoke | P0
RevealEvent | Messaging | created_at | timestamptz |  | P0
Notification | Notify | id | uuid v7 | PK | P0
Notification | Notify | persona_id | uuid | FK Persona, index | P1
Notification | Notify | kind | enum notification_kind |  | P0
Notification | Notify | payload | jsonb | no PII | P1
Notification | Notify | read_at | timestamptz | nullable | P0
Notification | Notify | created_at | timestamptz | index | P0
AdminUser | System | id | uuid v7 | PK | P0
AdminUser | System | created_at | timestamptz | not null | P0
AdminUser | System | updated_at | timestamptz | not null | P0
AdminUser | System | email | citext | unique | P2
AdminUser | System | role | enum admin_role |  | P0
AdminUser | System | totp_secret_enc | bytea |  | P3
AdminUser | System | active | bool |  | P0
AuditLog | System | id | uuid v7 | PK | P0
AuditLog | System | actor_type | enum actor_type |  | P0 | user/admin/system/ai
AuditLog | System | actor_id | uuid |  | P0
AuditLog | System | verb | varchar(48) |  | P0
AuditLog | System | target_type | varchar(32) |  | P0
AuditLog | System | target_id | uuid |  | P0
AuditLog | System | meta | jsonb | no raw PII | P0
AuditLog | System | created_at | timestamptz | index | P0
SecurityEvent | System | id | uuid v7 | PK | P0
SecurityEvent | System | kind | enum security_event_kind | index | P0
SecurityEvent | System | user_id | uuid | nullable | P3
SecurityEvent | System | ip_hash | bytea |  | P3
SecurityEvent | System | meta | jsonb |  | P0
SecurityEvent | System | created_at | timestamptz | index | P0
AiUsage | System | id | uuid v7 | PK | P0
AiUsage | System | purpose | enum ai_purpose |  | P0
AiUsage | System | model | varchar(48) |  | P0
AiUsage | System | input_tokens | int |  | P0
AiUsage | System | output_tokens | int |  | P0
AiUsage | System | cost_micros_usd | bigint |  | P0
AiUsage | System | user_id | uuid | nullable | P3 | for per-user caps
AiUsage | System | created_at | timestamptz | index | P0

## Enums
Enum | Values
user_status | active, suspended, banned, pending_deletion, deleted
gender | woman, man, non_binary, prefer_not_to_say
platform | ios, android
consent_purpose | core_service, travel_matching, ai_processing, analytics, marketing_push
dm_policy | requests, nobody
persona_intent | vent, listen, travel_buddy, friends, discuss
vibe_category | talk_style, music, sport, hobby, work, study, food, wellbeing
bowl_kind | city, line, station, office_hub, college, topic
bowl_visibility | public, members_only
bowl_role | member, moderator, owner
post_type | text, image, poll
content_status | visible, pending_review, removed_by_mod, removed_by_author, hidden_auto
vote_target | post, comment
conversation_kind | dm, group, crew, travel, discussion
conv_role | member, admin, owner
dm_context | post, comment, room, profile, episode
request_status | pending, accepted, ignored, blocked, expired
message_kind | text, image, system, meet_point
reveal_level | none, first_name, photo, contact
reveal_action | grant, revoke
content_type | persona, post, comment, message, conversation, episode, call_in, trip
pii_kind | phone, email, upi, aadhaar, pan, handle, url, address
detector | regex, llm
travel_mood | chatty, quiet, either
intent_status | active, matched, expired, cancelled
match_side_status | pending, accepted, declined
match_status | proposed, accepted, declined, expired
trip_status | planned, met, completed, no_show, cancelled
sos_status | open, contacts_notified, resolved, false_alarm
host_status | applied, approved, suspended, rejected
episode_status | scheduled, live, ended, cancelled
stage_role | host, co_host, on_air, listener
callin_status | queued, on_air, done, dropped, withdrawn
report_reason | harassment, hate, sexual, self_harm, spam, doxxing, threat, underage, impersonation, other
severity | low, medium, high, critical
case_status | open, in_review, actioned, dismissed, escalated
mod_action | remove_content, warn, mute_24h, suspend, ban, restore, revoke_host
appeal_status | open, upheld, overturned
grievance_category | content, privacy, impersonation, ncii, other
trust_event_kind | account_age, verified, report_upheld, report_dismissed, positive_feedback, no_show, safety_flag, mod_action
notification_kind | dm_request, message, reply, match, trip_reminder, episode_live, mod_notice, sos
admin_role | moderator, trust_safety_lead, admin
actor_type | user, admin, system, ai
security_event_kind | otp_fail, otp_throttle, refresh_reuse, permission_denied, rate_limited, vault_access
ai_purpose | pii_second_pass, moderation_triage, icebreaker, host_topics